## Sheet1
Issue Key | Summary | Description | Assignee | Status | Epic Link | Story Points | Priority | Created Date | Resolution Date | Last Updated
RFP-101 | Sales raises new RFP | Sales rep raises a request for proposal | Sales | To Do | RFP Intake & Qualification | 2 | High | 2025-07-01 | 2025-07-04 | 2025-07-04
RFP-102 | Validate client requirements | Review feasibility and scope of client RFP | BA | In Progress | RFP Intake & Qualification | 3 | Medium | 2025-07-01 | 2025-07-05 | 2025-07-05
RFP-103 | Assign RFP priority | BA sets priority based on value and timeline | BA | In Review | RFP Intake & Qualification | 2 | Medium | 2025-07-01 | 2025-07-06 | 2025-07-06
RFP-104 | Tag deal value and due date | Sales adds expected value and due date | Sales | Done | RFP Intake & Qualification | 1 | Low | 2025-07-01 | 2025-07-04 | 2025-07-04
RFP-201 | Break down RFP into tasks | BA assigns technical and documentation tasks | BA | In Progress | Proposal Development | 3 | High | 2025-07-02 | 2025-07-06 | 2025-07-06
RFP-202 | Draft technical solution | Solution Architect creates technical response | Architect | To Do | Proposal Development | 5 | High | 2025-07-02 | 2025-07-07 | 2025-07-07
RFP-203 | Checklist for documents | BA creates a submission checklist | BA | To Do | Proposal Development | 2 | Medium | 2025-07-02 | 2025-07-05 | 2025-07-05
RFP-204 | Create solution diagrams | Designer adds visuals to the proposal | Designer | To Do | Proposal Development | 3 | Low | 2025-07-02 | 2025-07-06 | 2025-07-06
RFP-301 | Review proposal draft | Proposal Manager does quality checks | Proposal Manager | To Do | Review & Approval | 3 | High | 2025-07-03 | 2025-07-08 | 2025-07-08
RFP-302 | Final approval by dept head | Department head signs off proposal | Dept Head | To Do | Review & Approval | 2 | High | 2025-07-03 | 2025-07-06 | 2025-07-06
RFP-303 | Collect review feedback | BA gathers reviewer comments for revision | BA | To Do | Review & Approval | 2 | Medium | 2025-07-03 | 2025-07-07 | 2025-07-07
RFP-401 | Submit proposal | BA submits final proposal before deadline | BA | To Do | Submission & Feedback | 1 | High | 2025-07-04 | 2025-07-09 | 2025-07-09
RFP-402 | Track RFP outcome | Sales updates result as Won/Lost | Sales | To Do | Submission & Feedback | 1 | Medium | 2025-07-04 | 2025-07-07 | 2025-07-07
RFP-403 | Update proposal status | BA marks ticket as Submitted, Won, or Lost | BA | To Do | Submission & Feedback | 1 | Medium | 2025-07-04 | 2025-07-08 | 2025-07-08
RFP-404 | Document reasons for loss | BA notes client feedback on lost bids | BA | To Do | Submission & Feedback | 2 | Low | 2025-07-04 | 2025-07-09 | 2025-07-09